## Slide 1
CHAITANYA BHARATHI INSTITUTE OF TECHNOLOGY (AUTONOMOUS), GANDIPET, HYDERABAD
Application for a Software Development Project
LabSubmit
A secure programming laboratory management, code execution and evaluation platform
Already built. Already deployed. In use today.
DEPARTMENT
CSE — IoT & Cyber Security
including Blockchain Technology
APPLICANTS
V Pranav — 160125749063
K Sai Rithvik Reddy — 160125749026
DURATION & BUDGET
12 months
₹ 89,000 requested
Submitted to the Head of the Department · Department of CSE (IoT & CSBCT), CBIT
Notes: Good morning. LabSubmit is a lab-submission and code-execution platform we have already built, deployed and used end to end. This proposal asks for support to take it from a working prototype to a production system the department can run for every programming lab.

## Slide 2
THE PROBLEM
The lab workflow today
Every lab session needs tasks issued, code verified and marks recorded. Today that work is split across email, pen drives and spreadsheets.
Fragmented submission
No central system for issuing tasks or collecting work — email and pen-drive handoffs.
No registration control
Authorised roll-number ranges are not enforced, leaving room for duplicate accounts.
No built-in execution
Faculty compile and run every submission manually on their own machine.
No anti-cheat protection
Nothing prevents copy-paste or external code reuse during a timed assessment.
No audit trail
Submission timestamps, evaluation status and feedback are not recorded consistently.
Manual grading
Marks live in spreadsheets — error-prone, with no real-time visibility for students.
Notes: Six concrete gaps in the current workflow. None of them are hypothetical — every one of them happens in our own lab sessions.

## Slide 3
THE SOLUTION
One platform, from registration to published grade
LabSubmit is a role-based web platform that replaces the entire lab workflow end to end.
Roll-number-gated registration against Admin-authorised ranges
Faculty-authored lab assignments with due dates and constraints
An in-browser IDE that compiles on the server, not the student's machine
Editor-level anti-cheat controls and automatic submission locking
Marks, remarks and status that students see in real time
5
languages compiled server-side
C, C++, Java, Python, JavaScript
3
role-based dashboards
Administrator, Faculty, Student
₹0
licence and development cost
Open-source stack, already built
1
live public deployment
Reviewable before anything is approved
Notes: The platform is not a concept. Every capability listed here is running today at labsubmit.vercel.app.

## Slide 4
WHO USES IT
Three roles, three dashboards, one system
The platform maps directly onto how CBIT already organises students — by 12-digit roll number, branch, year and section.
System Administrator
admin@cbit.in
Create and manage faculty accounts
Allocate authorised roll-number ranges
Institution-wide student directory
System metrics and grading completion
Faculty Lecturer
username@cbit.in
Create and manage sections
Author lab assessments and due dates
Review submissions and re-run code
Award marks, remarks and status
Student
12-digit CBIT roll number
Register against an authorised range
Write and run code in the browser IDE
Submit once — workspace auto-locks
See marks and feedback in real time
Notes: Three access levels. Every API endpoint re-verifies the caller's role, so a student cannot reach faculty or admin functions by manipulating a request.

## Slide 5
FEATURES · 1 OF 3
Administrator
Sets up the term and keeps institution-wide visibility.
Faculty management
Create, edit and delete lecturer accounts, set student capacity limits, reset passwords.
Roll-number allocation
Define authorised ranges (e.g. 160125000001–160125000120) and assign them to a lecturer.
Institution-wide directory
Every registered student across departments, sorted automatically by roll number.
Metrics and reporting
Total submissions, grading completion rates and performance statistics across faculty.
ONE-TIME SETUP
The term is configured once, in minutes.
After that, registration polices itself — out-of-range roll numbers simply cannot create an account.
Notes: The administrator does the least work of the three roles, and only at the start of a term.

## Slide 6
FEATURES · 2 OF 3
Faculty Lecturer
Authors labs, runs student code and grades — all in one panel.
Section management
Create, rename and delete sections for 1st–4th year students, such as CSE-1 or CIC-1.
Lab assessment authoring
Write problem statements, set due dates and specify input / output constraints.
Submission viewer & code runner
Inspect multi-file submissions, execute code live and download source files.
Evaluation & grading
Marks 0–100, remarks, status (Approved / Rejected / Needs Correction), reopen a workspace.
NO MANUAL COMPILATION
Code runs from the grading panel itself.
Faculty stop copying files onto their own machine to check whether a submission compiles.
Notes: This is the slide that matters most to lab faculty — it removes the manual compilation step entirely.

## Slide 7
FEATURES · 3 OF 3
Student
Registers, codes, submits and sees results — without leaving the browser.
Controlled self-registration
Validated against a 12-digit roll number inside an Admin-authorised range.
Monaco online IDE
Tabbed, multi-file editor with syntax highlighting for C, C++, Java, Python and JavaScript.
Anti-cheat protection
Copy, paste, cut, right-click, shortcuts and drag-and-drop are blocked; fullscreen exits are logged.
Single-submission locking & live grades
The workspace turns read-only on submit; published marks and remarks appear immediately.
THE ORIGINAL MOTIVE
Stop copy-paste during a timed assessment.
The platform supplements invigilation rather than replacing it — flagged events go to the lecturer.
Notes: Anti-cheat was the original motive for building LabSubmit. We are candid that it is browser-level: a determined student with a second device is still a job for invigilation.

## Slide 8
ARCHITECTURE & STACK
Built on open-source, self-hostable throughout
No licensing cost to the institution at any layer. The same Docker image runs on cloud hosting or a college virtual machine.
Frontend
Next.js 14 · TypeScript · Tailwind
Admin, faculty and student portals
Code editor
Monaco Editor
Multi-file in-browser IDE, 5 languages
Backend / API
Next.js API routes · ws · node-pty
REST endpoints, live terminal
Database / ORM
Prisma ORM · PostgreSQL
Users, labs, submissions, grades
Authentication
JWT · bcryptjs
Role-based tokens, hashed passwords
Execution engine
Docker · GCC, G++, JDK 17, Python 3, Node
Compiles and runs every submission
Deployment
Vercel + Railway · Docker
Also runs unchanged on a college VM
Notes: Every component is MIT, Apache 2.0 or GPL. There are no per-student seats and no vendor lock-in.

## Slide 9
HOW IT RUNS AT CBIT
A lab session, end to end
Nothing changes about how students are identified administratively — the platform is built around CBIT's existing roll-number and section structure.
1
Admin sets up the term
Faculty accounts created; roll-number range defined and assigned to each lecturer.
2
Students self-register
Validated live against the assigned range — out-of-range sign-ups are rejected.
3
Lecturer authors the lab
Sections created; problem statement, constraints and due date published.
4
Students code in the browser
Compile and run live against the execution engine, anti-cheat active throughout.
5
Submit and auto-lock
The workspace becomes read-only immediately, preserving submission integrity.
6
Faculty grade
Re-run code, assign marks, remarks and status — publish, or reopen for correction.
7
Results and reporting
Students see grades in real time; the Admin pulls department-wide metrics.
Notes: Seven steps. The lab session a lecturer runs today with pen drives and a personal laptop becomes these seven steps inside one platform.

## Slide 10
NOT A PROTOTYPE AWAITING FUNDING
It is deployed and reachable right now
The committee can open it, log in and use it before deciding anything. Reviewer credentials are supplied separately.
labsubmit.vercel.app
Live platform · HTTPS/TLS enforced on every request
github.com/vudigapranav/LabSubmit
Full source available for institutional review
Application hosting
Vercel — web interface and all REST API endpoints
Execution engine
Railway — compiler container: GCC, G++, OpenJDK 17, Python 3, Node.js
Database
Managed PostgreSQL, all data encrypted in transit
Encryption
HTTPS/TLS on every request; certificates auto-renewed
The two hosts are split by necessity, not preference: compiling student code needs a persistent process with real compilers attached. Students and faculty see one website.
Notes: Please do open it during or after this presentation. Everything claimed in the previous slides can be checked directly.

## Slide 11
WORK PLAN
Twelve months, five phases
PERT sequence P1 → P2 → P3 → P4 → P5. The critical path runs through all five phases; P3 overlaps P2 by one month and carries one month of float.
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
M11
M12
P1
Requirement study & rubric
Requirement and rubric document
M1 – M2
P2
Execution-engine hardening
Isolated per-student execution engine
M2 – M5
P3
Integrity & faculty tooling
Integrity and evaluation suite
M4 – M7
P4
Load & security testing
Load and security test report
M7 – M9
P5
Pilot, rollout & handover
Deployed platform + handover kit
M9 – M12
Handover: source code, database schema, deployment guide and administrator manual are delivered to the Department, so later project batches can maintain the platform without the original authors.
Notes: Twelve months. P3 starts before P2 finishes, once the sandbox is functional — that overlap is deliberate and is the only float in the plan.

## Slide 12
PROPOSED BUDGET
₹ 89,000 for twelve months
All figures in Indian Rupees. No equipment purchase is requested — LabSubmit runs in a browser, so lab computers need no compilers, IDEs or installation.
Chart: 
| Manpower — student honorarium | Execution engine + database | Application hosting (web + API) | AI / LLM API services | Backups, monitoring, load testing | Domain, SSL and contingency
Budget | 36000 | 22800 | 11400 | 9000 | 6000 | 3800
₹89,000
total, 12 months
Manpower — student honorarium
2 developers × ₹2,000 × 9 months
₹ 36,000
Execution engine + database
Always-on container, ~₹1,900/month
₹ 22,800
Application hosting (web + API)
Vercel Pro, ₹1,900 × 6 active months
₹ 11,400
AI / LLM API services
Similarity explanation, ~₹750/month
₹ 9,000
Backups, monitoring, load testing
Snapshots, alerting, staging resources
₹ 6,000
Domain, SSL and contingency
₹0 if college IT issues the subdomain
₹ 3,800
TOTAL PROPOSED BUDGET
₹ 89,000
Licence cost ₹0 and development cost ₹0 — every component is open-source and the platform is already built. · No equipment purchase and no cost to students at any point.
Notes: Eighty-nine thousand for the year. Just over half of it is the student honorarium at institute norms; the rest is infrastructure that we can show line by line.

## Slide 13
THREE-YEAR VIEW
What it costs after the grant year
Two honest paths. The cheaper one is not the one that gets the platform running fastest, so we recommend starting with A and migrating to B.
A
Stay on commercial cloud
Year 1 — grant year
₹ 89,000
Year 2 — full department
₹ 53,000
Year 3 — 2–3 departments
₹ 53,000
3-year total
₹ 1,95,000
B
Cloud year one, then college VM
Year 1 — grant year
₹ 89,000
Year 2 — migrate to college VM
₹ 0
Year 3 — steady state
₹ 0
3-year total, if a VM is available
₹ 89,000
Recommendation — begin on the cloud, migrate to campus infrastructure once the platform has proven itself. Recurring cost falls to almost nothing, student data stays physically within the institution, and the move pays for itself inside the second year.
Notes: Scenario B is where we want to end up. The platform already ships as a Docker container, so the migration is a deployment task, not a rewrite.

## Slide 14
RISKS & LIMITATIONS
Stated plainly, with the mitigation for each
The platform is presented as it actually is, including where it is not yet ready. The pilot exists so these limits are tested at small scale rather than discovered during a graded examination.
No isolation between running submissions
Student code runs as an ordinary process in a shared container — one infinite loop can slow the session.
Mitigation Per-student CPU, memory and time limits are the first priority of this project (Phase P2).
Concurrent load at department scale untested
Behaviour with 300 simultaneous compilations has not yet been measured.
Mitigation Load testing at 60 and 300 concurrent compilations in Phase P4, before any wider commitment.
Anti-cheat is browser-level only
Copy, paste and shortcuts are blocked, but a determined student can use a second device.
Mitigation The platform supplements invigilation; fullscreen-exit counts are recorded and flagged to the lecturer.
Single-maintainer dependency
The platform currently has one developer, who will eventually graduate.
Mitigation Source code, schema and deployment documentation are handed to the Department in Phase P5.
Notes: We would rather bring these to the committee ourselves than have them found later. Each one maps to a phase in the work plan.

## Slide 15
THE ASK
Approve ₹ 89,000 over twelve months
and one pilot section.
Production-hardened
Per-student sandboxes with CPU, memory and process limits, plus an execution queue.
Integrity module
Similarity comparison across a section, telemetry, and AI-drafted remarks for faculty review.
Accreditation-ready
Exportable mark sheets and submission trails for NBA / NAAC outcome-based reporting.
Handed to the Department
Source code, schema, deployment guide and administrator manual — no vendor, no lock-in.
One platform replaces pen-drive submissions, manual compilation and spreadsheet grading — across every lab session, in every section, for ₹89,000 a year.
V Pranav · 160125749063 · K Sai Rithvik Reddy · 160125749026 · Department of CSE (IoT & CSBCT), CBIT · labsubmit.vercel.app
Notes: Thank you. We are happy to demonstrate the live platform now, and to answer questions on the sandbox design or the budget line items.